## Projects
Projects Master Tracker
Project ID | Opportunity | Category | Status | Stage | Lead | Partner / Sponsor | Focus Area | Submission Date | Deadline | Funding Amount | Funding Currency | Notes | Updated At | Updated By
PRJ-001 | Amref - resubmitted | In Process | Through to next round | In Process | Go | Amref | General | 2026-01-09 | 2026-02-28 | 50000 | USD | Through to next round.
PRJ-002 | EDCTP Global collaboration action | In Process | In process | Stage 1 Submission | FV | EDCTP / Utrecht / Heidelberg / Amsterdam | HIV / Comorbidity |  | 2026-03-04 | 5000000 | EUR | Two-stage application.
PRJ-003 | Three other EDCTP opportunities | In Process | In process | In Process | Various | EDCTP | HIV / Cannabis / Comorbidity |  | 2026-03-04 |  | Unknown | Cannabis, HIV cure, comorbidity.
PRJ-004 | NIH R21/33: RISE | In Process | Due soon | Proposal Development | Nicola Bulled / Wits | NIH / UMass | HIV / Comorbidity |  | 2026-03-15 |  | Unknown | Low-resource urban communities in South Africa.
PRJ-005 | Wellcome Discovery 2 | In Process | Review discussion ongoing | Review / Rework | FV / Jen / Suman | Wellcome | Research |  | 2026-03-31 |  | Unknown | Review meeting completed.
PRJ-006 | Wellcome Discovery 1 Reloaded | In Process | Concept submitted | Concept / Reapply | FV / Jenn / Holly | Wellcome | Research |  | 2026-07-31 |  | Unknown | July 2026 target round.
PRJ-007 | Wellcome Clinical Trials | In Process | Call expected | Watchlist | FV | Wellcome | Clinical Trials |  |  |  | Unknown | Possible generic Sema study.
PRJ-008 | CHAI Len/CAB switch/naive | In Process | Concept circulated | Concept | FV | CHAI / Gates | Len / HIV |  |  | 3000000 | USD | Additional $2m may be needed.
PRJ-009 | Novo obesity trials opportunity | In Process | Concept to be written | Concept | Tarryn / Alison | Novo | Obesity |  |  |  | Unknown | Investigator-led studies.
PRJ-010 | Chinese Pharmaceutical | In Process | Unfunded for now | Early Discussion | Francois / Simiso | Chinese Pharmaceutical | Pharma |  |  |  | Unknown | Roger Bedimo wants to chat.
PRJ-011 | London Growth Capital / Baby Trump | In Process | Monitoring | Watchlist | Nkuli | London Growth Capital | Sepsis |  |  |  | Unknown | Probably not a fit.
PRJ-012 | Merck CRO / Oncology HIV study | In Process | Looking into it | Early Review | Nkuli | Merck | Oncology / HIV |  |  |  | Unknown | Review underway.
PRJ-013 | Eli Lilly diabetes and obesity projects | In Process | Follow-up required | Follow-up | Nkuli | Eli Lilly | Diabetes / Obesity |  |  |  | Unknown | Further viability check needed.
PRJ-014 | Sema/Cagril Pharma study | In Process | Contract coming | Contracting | Simiso | Pharma | Sema / Cagril |  |  |  | Unknown | 15–20 participants.
PRJ-015 | FHI 360 long-acting prevention | In Process | Follow-up needed | Follow-up | Francois / Hally / Chris | FHI 360 | Prevention |  |  |  | Unknown | Meeting follow-up required.
PRJ-016 | EDCTP - PK, Reg Ethics capacity | In Process | Likely August submission | Planning | Nkuli | EDCTP / NEPAD | Capacity Building |  | 2026-08-15 |  | Unknown | 1-stage application.
PRJ-017 | Phoenix group quotes | In Process | None presently | Dormant | Mo | Phoenix Group | Quotes |  |  |  | Unknown | Discuss with Mo.
PRJ-018 | University of British Columbia - small application | In Process | Submitted on our behalf | Submitted | Nkuli / Jamie Forrest | University of British Columbia | Academic |  |  |  | Unknown | Small application.
PRJ-019 | MISP - opti dor | In Process | In process | In Process | Unknown | MISP | MISP |  |  | 1000000 | USD | Approx $1m.
PRJ-020 | Gates Grand Challenges - AI decision support | New Opportunity | For consideration | New Opportunity | TBD | Gates | AI / Primary Care |  |  | 3000000 | USD | Pathway A and B available.
PRJ-021 | Leeds-Wits Horizons platform | New Opportunity | For consideration | New Opportunity | TBD | Leeds-Wits | Climate and Health |  |  |  | Unknown | Three small opportunities.
PRJ-022 | GACD 11th funding round - Joint Process | New Opportunity | Suggested go | New Opportunity | Sam | GACD | Multisectoral approaches |  | 2026-06-17 |  | Unknown | Use Healthy Jozi phase 1 learnings.
PRJ-023 | UK MRC partnership grant | New Opportunity | Co-lead only | New Opportunity | TBD | UK MRC | Research Grant |  |  |  | Unknown | Rolling submission.
PRJ-024 | UK MRC research grant | New Opportunity | Co-lead only | New Opportunity | TBD | UK MRC | Research Grant |  |  |  | Unknown | Rolling submission.
PRJ-025 | PATH opportunities with Kim | New Opportunity | Email discussion | New Opportunity | Mo | PATH | Len / Dx / Pharmacy Health |  |  |  | Unknown | Discussion ongoing.
PRJ-026 | 5FC - Jeremy Nel | New Opportunity | Explore as EzCRO | New Opportunity | Nkuli | 5FC | EzCRO |  |  | 300000 | ZAR | R300,000 opportunity.
PRJ-027 | PICASSO 2 for Len | New Opportunity | For consideration | New Opportunity | Francois / Simiso | PICASSO 2 | Len |  |  |  | Unknown | For Len.
PRJ-028 | GES Labs cannabis work | New Opportunity | Next step call | New Opportunity | TBD | GES Labs | Cannabis |  |  |  | Unknown | Call with Peter Nel and team.
PRJ-029 | Wellcome early career award | Submitted - Awaiting Decision | Awaiting decision | Submitted | Spha | Wellcome | Early Career | 2026-02-16 |  |  | Unknown | Awaiting decision.
PRJ-030 | Multiplex/Diagnostics Unitaid | Submitted - Awaiting Decision | Submitted | Submitted | Ezintsha / PSI | Unitaid | Diagnostics | 2026-01-29 |  |  | Unknown | Ezintsha prime, PSI support.
PRJ-031 | BioEquivalence Morphine Sulphate Oral products | Submitted - Awaiting Decision | Budget submitted | Submitted | TBD | Unknown | Bioequivalence | 2026-01-19 |  | 500000 | USD | Approx $500,000.
PRJ-032 | Merck MISP Sleep | Submitted - Awaiting Decision | Review comments addressed | Submitted | Tarryn | Merck | Sleep | 2025-11-17 |  |  | Unknown | Reviewer comments addressed.
PRJ-033 | Open Society Foundations - IMITHI concept | Submitted - Awaiting Decision | Waiting on OSF | Submitted | Nkuli | Open Society Foundations | IMITHI | 2025-10-15 |  |  | Unknown | Tricky sell.
PRJ-034 | SA MRC SIR grant - iHEART follow up | Submitted - Awaiting Decision | Awaiting decision | Submitted | Spha | SA MRC | iHEART |  |  |  | Unknown | Follow up.
PRJ-035 | University of British Columbia - small application | Submitted - Awaiting Decision | Submitted on our behalf | Submitted | Jamie Forrest | University of British Columbia | Academic |  |  |  | Unknown | Small application.
PRJ-036 | Talisman 2/IMPRESS | Recent Decision | Not successful | Decision | Sam | Unknown | Research | 2025-09-16 |  |  | Unknown | Not successful.
PRJ-037 | HERO vaccine work | Recent Decision | Cancelled | Decision | Simiso | NIH | Vaccine |  |  | 20000 | USD | Funding withdrawn.
PRJ-038 | COMBAT Trial | Recent Decision | Not successful | Decision | Unknown | Unknown | Clinical Trial |  |  |  | Unknown | Not successful.
PRJ-039 | Gilead INCLUSION | Recent Decision | No go | Decision | PSI | Gilead | Inclusion | 2026-01-30 |  |  | Unknown | Budget small, drug unavailable.
PRJ-040 | ANRS | Recent Decision | Not successful | Decision | FV / Tarryn | ANRS | Research | 2025-09-15 |  |  | Unknown | To discuss.
PRJ-041 | HBNU Fogarty Global Health Fellowship | Recent Decision | Not successful | Decision | Spha / Sam | Fogarty | Global Health Fellowship |  |  |  | Unknown | May repurpose concept.